## Bug Report (hidden)
Victoria | BUG REPORT FOR Cycluno AI-Powered Test Automation Platform |  |  | Funmilola | BUG REPORT FOR Cycluno AI-Powered Test Automation Platform
| Bug ID | ID Number & Feature | Bug-01 / Login |  | Bug ID | ID Number & Feature | Bug-02/ Registration
|  | Bug Name | Website fails to resolve on mobile carrier default DNS (NXDOMAIN error) |  |  | Bug Name | Missing Verification Link After Registration
|  | Reported By: | Adu Victoria |  |  | Reporter By: | Funmilola Bolarinwa
|  | Submission Date | 2026-02-26 |  |  | Submission Date | 2024-02-26
| Bug Overview | Summary | Website is inaccessible when accessed via mobile carrier default DNS, returning NXDOMAIN error. Site loads successfully when using public DNS (Cloudflare 1.1.1.1) on mobile chrome only but not on latop. |  | Bug Overview | Summary | After completing the registration process successfully, the system did not send a verification email containing a clickable verification link as expected. Instead, only a verification code was received. If the system requirement specifies sending a verification link, this indicates a functional defect in the email verification process.
|  | URL | https://cycluno.com/dashboard |  |  | URL | https://cycluno.com/login
| Bug Details | Steps to Reproduce |  |  | Bug Details | Steps to Reproduce | - Navigate to the application’s Registration / Sign Up page
|  | 1 | Connect iPhone to mobile data (carrier default DNS enabled). |  |  | 1 | Enter valid user details (e.g., email, password, and required fields).
|  | 2 | Ensure no public DNS (e.g., 1.1.1.1) or VPN is active |  |  | 2 | Click on the Sign Up / Register button.
|  | 3 | Open Chrome and firefox on laptop and phone |  |  | 3 | Observe the confirmation message (if displayed).
|  | 4 | Enter the website URL (e.g., https://cycluno.com) |  |  | 4 | Open the registered email inbox.
|  | 5 | Observe the result. |  |  | 5 | Check both the Inbox and Spam/Junk folders.
|  | Actual Result | The website did not open until 1.1.1.1 cloudflare was activated The browser displays: DNS_PROBE_FINISHED_NXDOMAIN on the laptop and stops loading with no display on the phone |  |  | 6 | Review the email received from the system.
|  | Expected Result | The website should resolve correctly and load successfully when accessed via mobile data using default carrier DNS on phone and laptop. |  |  | Actual Result | A verification email containing a clickable verification link should be sent to the registered email address immediately after successful registration
| Environment | Browser | Chrome and Firefox |  |  | Expected Result | A verification email containing a clickable verification link should be sent to the registered email address immediately after successful registration
|  | Oerating System | Windows PC |  | Environment | Browser | Chrome/Firefox
|  | Network | MTN 5G / Airtel pocket mifi |  |  | Operating System | Windows 11
|  | Device | HP Elitebook 840 g4 / iPhone 12 |  |  | Network | MTN 4G Wifi
| Bug Tracking | Severity | Critical |  |  | Device | Latitude 7480, Intel Core i5
|  | Priority | High |  | Bug Tracking | Severity | High
|  | Assigned To | Adu Victoria |  |  | Priority | High
| Status | To do | To do |  |  | Assigned To | Bisola Oyetade
| Attachments / Screenshot | Video or screen short | BUG 01 |  | Status | To do | To-do
| Note/Comment |  | Issue does not occur when switching DNS to: 1.1.1.1 (Cloudflare) 8.8.8.8 (Google DNS) Likely related to ISP DNS negative caching or propagation delay. Not reproducible on other networks. |  | Attachments / Screenshot | Video or screen short | Bug 16& 17.mp4
[5 empty] | Note/Comment |  | After successful registration, the system sent only a verification code instead of a clickable verification link as designed. This means the user has no clear way to verify their account since there is no visible field or instruction on where to enter the code. Combined with Reg_17, where the resend feature is also non-functional, the user is left completely unable to complete the verification process through any available path. This defect affects all newly registered users across both Chrome and Firefox and must be treated as a Critical blocker requiring immediate resolution before the next release cycle.
Emeka | BUG REPORT FOR Cycluno AI-Powered Test Automation Platform |  |  | Bisola | BUG REPORT FOR Cycluno AI-Powered Test Automation Platform
| Bug ID | ID Number & Feature | Bug-03 / Registration |  | Bug ID | ID Number & Feature | Bug-04 / Log-in
|  | Bug Name | Successfully signed up user with valid credentials, unable to sign in account due to wrong verification email sent |  |  | Bug Name | Navigation from "Get started for free" goes to "Sign in" instead of "Sign up / Registration Page"
|  | Reported By: | Emeka Nnadika |  |  | Reporter By: | Bisola Oyetade
|  | Submission Date | 2026-02-26 |  |  | Submission Date | 2026-02-26
| Bug Overview | Steps to Reproduce | Unable to Sign in account due to wrong verification email sent, a 6-digit code is sent instead of a 4 digit code |  | Bug Overview | Summary | - The 'Get Started for Free' call-to-action (CTA) button in the hero section is the primary conversion button on the page and is intended to drive new visitors toward creating a new account. - When the 'Get Started for Free' button is clicked, the user is redirected to the Sign In page (https://cycluno.com/login) rather than the Sign Up / Registration page (https://cycluno.com/register). This is incorrect behaviour. A first-time visitor clicking 'Get Started for Free' has no account yet and has expressed intent to register, sending them to the Sign In page instead creates immediate confusion, friction, and a broken user journey.
|  | URL | https://cycluno.com/register |  |  | URL | https://cycluno.com/
| Bug Details | Steps to Reproduce |  |  | Bug Details | Steps to Reproduce
|  | 1 | User successfully signs up and inputs the correct login details. |  |  | 1 | Navigate to Cycluno homepage
|  | 2 | User expects to log in to view the dashboard. |  |  | 2 | Click on the "Get started for free" tab
|  | 3 | User is redirected to the registered email for the verification link, only to get a four-digit code |  |  | 3 | Observe result
|  | 4 | There's no provision for the code.
|  | 5 | The user is unable to login to the dashboard
|  | Actual Result | A verification email containing a four digit code is sent |  |  | Actual Result | "Get Started for Free" tab should redirect user to the "Sign up/ Register" page to get started as a new users just as the feauture implies
|  | Expected Result | A verification email containing a "link" to the account since the login details are correct |  |  | Expected Result | Redirects the user to the "Sign-in" for existing users
| Environment | Browser | Chrome/ Firefox |  | Environment | Browser | Firefox and Chrome
|  | Operating System | Windows 11 |  |  | Operating System | Windows 11
|  | Network | MTN |  |  | Network | MTN 5G WIFI
|  | Device | HP desktop |  |  | Device | LENOVO THINKPAD, I5
| Bug Tracking | Severity | Medium |  | Bug Tracking | Severity | Medium
|  | Priority | Medium |  |  | Priority | Medium
|  | Assigned To | Wisdom Achi |  |  | Assigned To | Hafeezat Abati
| Status | To do | To do |  | Status | To do | To do
| Attachments / Screenshot | Video or screen short | BUG 03 .webm |  | Attachments / Screenshot | Video or screen short | BUG 04.mp4
| Note/Comment |  | This defect affects both new and existing users with fully correct credentials. The system accepts the details but fails to deliver any verification email, resend option, or redirect — leaving all affected users permanently locked out. Must be treated as a Critical blocker before any release consideration. |  | Note/Comment |  | This is most likely a single-line fix in the homepage HTML or template code.
Akanimo | BUG REPORT FOR Cycluno AI-Powered Test Automation Platform |  |  | Sadiq | BUG REPORT FOR Cycluno AI-Powered Test Automation Platform
| Bug ID | ID Number & Feature | Bug-07 |  | Bug ID | ID Number & Feature | Bug-06 / Exploratory Test
|  | Bug Name | Error message on dashboard page |  |  | Bug Name | Two spelling errors
|  | Reporter By: | AKANIMO AKPABIO |  |  | Reporter By: | Sadiq Balgoun
|  | Submission Date | 2026-02-26 |  |  | Submission Date | 2026-02-26
| Bug Overview | Summary | Dashboard page displays no feautures but an error message |  | Bug Overview | Summary | The following texts are misspelled, Text ----- Test Visulaizations -------- Visualisations
|  | URL | https://cycluno.com/dashboard |  |  | URL | https://cycluno.com
| Bug Details | Steps to Reproduce |  |  | Bug Details | Steps to Reproduce
|  | 1 | Navigate to registration page (sign in) |  |  | 1 | Naviagte to cycluno homepage
|  | 2 | Log in to the account with existing username and password |  |  | 2 | Under the "Ship quality software......" heading
|  | 3 | Observe the result |  |  | 3 | The first line reads, "Automatically......., execute TEXT,...."
[6 empty] | 4 | Scroll down on the homepage to "insightful report"
[6 empty] | 5 | The last line reads "with beautiful visulaizations"
|  | Actual Result | Displays error message "we ran into a problem loading your workspace. Please try again,. Your data is still safe. You can retry or navigate back to the dashboard home". |  |  | Actual Result | Spelling errors in two different places
|  | Expected Result | Should show feautures of the dashboard |  |  | Expected Result | No spelling error
| Environment | Browser | Chrome and Firefox |  | Environment | Browser | Chrome and Firefox
|  | Operating System | Windows 11 PC |  |  | Operating System | WINDWOS 11 PRO
|  | Network | GLO 4G ROUTER |  |  | Network | STARLINK
|  | Device | SAMSUNG LAPTOP |  |  | Device | DELL 7280 Intel corei5
| Bug Tracking | Severity | High |  | Bug Tracking | Severity | Low
|  | Priority | Major |  |  | Priority | Minor
|  | Assigned To | Emeka Nnadika |  |  | Assigned To | AKANIMO AKPABIO
| Status | To do | To do |  | Status | To do | To do
| Attachments / Screenshot | Video or screen short | BUG 05.png |  | Attachments / Screenshot | Video or screen short | BUG 06
| Note/Comment |  |  |  | Note/Comment |  | This is most likely a single-line fix in the homepage HTML or template code.
Hafeezah | BUG REPORT FOR Cycluno AI-Powered Test Automation Platform |  |  | Wisdom | BUG REPORT FOR Cycluno AI-Powered Test Automation Platform
| Bug ID | ID Number & Feature | Bug-07 / Registration |  | Bug ID | ID Number & Feature | Bug-08 / Exploratory test
|  | Bug Name | "Create account" button is not disabled when all mandatory fields are not filled yet. |  |  | Bug Name | "Upgrade" and "Settings" buttons do not redirect / navigate to their respective screens/prompts when clicked
|  | Reported By: | Hafeezat Abati |  |  | Reporter By: | Joseph Wisdom Achi
|  | Submission Date | 2026-02-24 |  |  | Submission Date | 26th February, 2026
| Bug Overview | Summary | The "Create Account" button remained blue throughout the filing process instead of being greyed out while filling the mandatory fields. |  | Bug Overview | Summary | The "Upgrade" and "Settings" buttons are currently non-responsive; clicking them fails to trigger the expected redirection or launch the respective prompts. Despite appearing active in the UI, both elements remain stagnant, effectively blocking user access to subscription management and account configuration panels.
|  | URL | https://cycluno.com/register |  |  | URL | https://cycluno.com/
| Bug Details | Steps to Reproduce |  |  | Bug Details | Steps to Reproduce
|  | 1 | Navigate to the signup page |  |  | 1 | Click / tap the "Upgrade" button.
|  | 2 | leave one or more mandatory fields blank |  |  | 2 | Observe the result.
|  | 3 | Observe the "create account" button |  |  | 3 | Click / tap the "Settings" button.
[6 empty] | 4 | Observe the result.
|  | Actual Result | The button is fully enabled and clickable despite missing information. |  |  | Actual Result | Clicking the "Upgrade or Setting"button does nothing (no navigation, no prompt/modal appears, no new screen loads). No error message is shown to the user.
|  | Expected Result | The button should be greyed out or disabled until all fields are fiiled. |  |  | Expected Result | Clicking either the "Upgrade" or "Settings" buttons should immediately trigger a redirection to their respective destinations, following a brief, standard loading state.
| Environment | Browser | Chrome and Firefox |  | Environment | Browser | Chrome
|  | Operating System | Windows 11 PC |  |  | Operating System | Windows 11 Pc.
|  | Network | Airtel 4G pocket Wifi |  |  | Network | MTN-5G/Airtel 4G Router
|  | Device | HP Elitebook |  |  | Device | Thinkpad Lenovo PC
|  | Severity | Low |  |  | Severity | Low
|  | Priority | Minor |  |  | Priority | Minor
|  | Assigned To | Sadiq Balogun |  |  | Assigned To | Funmilola Bolarinwa
| Status | To do | To do |  | Status | To do | To do
| Attachments / Screenshot | Video or screen short | BUG 07.docx |  | Attachments / Screenshot | Video or screen short | Bug Video/Picture-Upload
| Note/Comment |  | The "Create Account" button lacks proper UI validation. It currently remains enabled even if mandatory fields are blank.this button should stay disabled (greyed out) until the form requirements are met to prevent premature submission and unnecessary error triggers. |  | Note/Comment |  | This is most likely a single-line fix in the homepage HTML or template code.
Victoria & Wisdom | BUG REPORT FOR Cycluno AI-Powered Test Automation Platform
| Bug ID | ID Number & Feature | Bug-09 / Exploratory test
|  | Bug Name | Links in the feauture section redirect to an error page on the dashboard
|  | Reported By: | Adu Victoria
|  | Submission Date | 2026-02-26
| Bug Overview | Summary | Links under "feauture" section in the footer tab are redirected to dashboard which shows an error message
|  | URL | https://cycluno.com
| Bug Details | Steps to Reproduce
|  | 1 | Enter the website URL (e.g., https://cycluno.com)
|  | 2 | Scroll down to the footer
|  | 3 | Find the features section
|  | 4 | Click all four feautures listed (Design, Execute, Report, Bugbed)
|  | 5 | Observe the result.
|  | Actual Result | Redirected to dashboard showing the error message "dashboard issue - we ran into a problem loading your page"
|  | Expected Result | The tabs in the footer should redirect to respective options
| Environment | Browser | Chrome and Firefox
|  | Operating System | WindowsPC
|  | Network | MTN 5G / Airtel pocket mifi
|  | Device | HP Elitebook
| Bug Tracking | Severity | Medium
|  | Priority | Medium
|  | Assigned To | Wisdom Achi
| Status | To do | To do
| Attachments / Screenshot | Video or screen short | BUG 09.webm
| Note/Comment |  | This is most likely a content fix in the HTML or template code.

## Bug Reporting
CYCLUNO AI-POWERED TEST AUTOMATION PLATFORM BUG REPORT
Severity |  |  |  | Priority
Minor | 3 |  |  | Low | 3
Major | 5 |  |  | Medium | 3
Critical | 1 |  |  | High | 3
Total | 9 |  |  | Total | 9
Bug ID | Bug Summary | Bug Description | Steps to Reproduce | Test data | Expected result | Actual result | Severity | Priority | Evidence | Environment | Identified By | Date Identified
REGISTRATION
Bug-01 | "Create account" button is not disabled when all mandatory fields are not filled yet. | The "Create Account" button remained blue throughout the filing process instead of being greyed out while filling the mandatory fields. | Navigate to the signup page leave one or more mandatory fields blank Observe the "create account" button | https://cycluno.com/register | The button should be greyed out or disabled until all fields are filled. | The button is fully enabled and clickable despite missing information. | MINOR | LOW | BUG 01.docx | Chrome and Firefox Windows 11 PC Airtel 4G pocket Wifi HP Elitebook | Hafeezat Abati | 2026-02-24
Bug-02 | Missing Verification Link After Registration | After completing the registration process successfully, the system did not send a verification email containing a clickable verification link as expected. Instead, only a verification code was received. If the system requirement specifies sending a verification link, this indicates a functional defect in the email verification process. | 1. Navigate to the application’s Registration / Sign Up page 2. Enter valid user details (e.g., email, password, and required fields). 3. Click on the Sign Up / Register button. 4. Open the registered email inbox. 5. Check both the Inbox and Spam/Junk folders. 6. Review the email received from the system. | https://cycluno.com/login | A verification email containing a clickable verification link should be sent to the registered email address immediately after successful registration | A verification email containing a clickable verification link should be sent to the registered email address immediately after successful registration | MAJOR | HIGH | Bug 16& 17.mp4 | Chrome/Firefox Windows 11 MTN 4G Wifi Latitude 7480 Intel Core i5 | Funmilola Bolarinwa | 2026-02-24
Bug-03 | Successfully signed up user with valid credentials, unable to sign in account due to wrong verification email sent | Unable to Sign in account due to wrong verification email sent, a 6-digit code is sent instead of a 4 digit code | User successfully signs up and inputs the correct login details. User expects to log in to view the dashboard. User is redirected to the registered email for the verification link, only to get a four-digit code . There's no provision for the code. The user is unable to login to the dashboard | https://cycluno.com/register | A verification email containing a "link" to the account since the login details are correct | A verification email containing a four digit code is sent | MAJOR | MEDIUM | bug 3 | Browser: Chrome/ Firefox Operating System: Windows 11 Network: MTN Device: HP desktop | Emeka Nnadika | 2026-02-25
LOG-IN
Bug-04 | Website fails to resolve on mobile carrier default DNS (NXDOMAIN error) | Website is inaccessible when accessed via mobile carrier default DNS, returning NXDOMAIN error. Site loads successfully when using public DNS (Cloudflare 1.1.1.1) on mobile chrome only but not on latop. | 1. Connect iPhone to mobile data (carrier default DNS enabled). 2. Ensure no public DNS (e.g., 1.1.1.1) or VPN is active 3. Open Chrome and firefox on laptop and phone 4. Enter the website URL (e.g., https://cycluno.com) 5.Observe the result. | https://cycluno.com/dashboard | The website should resolve correctly and load successfully when accessed via mobile data using default carrier DNS on phone and laptop. | The website did not open until 1.1.1.1 cloudflare was activated The browser displays: DNS_PROBE_FINISHED_NXDOMAIN on the laptop and stops loading with no display on the phone | CRITICAL | HIGH | BUG 04 | Chrome and Firefox Windows PC | Victoria Adu | 2026-02-26
Bug-05 | Error message on dashboard page | Dashboard page displays no feautures but an error message | 1. Navigate to registration page (sign in) 2. Log in to the account with existing username and password 3. Observe the result | https://cycluno.com/dashboard | Should show feautures of the dashboard | Displays error message "we ran into a problem loading your workspace. Please try again,. Your data is still safe. You can retry or navigate back to the dashboard home". | MAJOR | HIGH | BUG 05.png | Chrome and Firefox Windows PC | Akanimo Akpabio | 2026-02-26
Bug-06 | "Upgrade" and "Settings" buttons do not redirect / navigate to their respective screens/prompts when clicked | The "Upgrade" and "Settings" buttons are currently non-responsive; clicking them fails to trigger the expected redirection or launch the respective prompts. Despite appearing active in the UI, both elements remain stagnant, effectively blocking user access to subscription management and account configuration panels. | 1.Click / tap the "Upgrade" button. 2.Click / tap the "Upgrade" button. 3. Observe the result. 3. Click / tap the "Settings" button. 4. Observe the result. | https://cycluno.com/ | Clicking either the "Upgrade" or "Settings" buttons should immediately trigger a redirection to their respective destinations, following a brief, standard loading state. | Clicking the "Upgrade or Setting"button does nothing (no navigation, no prompt/modal appears, no new screen loads). No error message is shown to the user. | MINOR | LOW | Bug Video/Picture-Upload | Browser: Chrome Operating System: Windows 11 Pc. Network: MTN-5G/Airtel 4G Router Device: Thinkpad Lenovo PC | Joseph Wisdom Achi | 2026-02-26
HOMEPAGE & DASHBOARD
Bug-07 | Two spelling errors | The following texts are misspelled, Text ----- Test Visulaizations -------- Visualisations | 1. Naviagte to cycluno homepage 2. Under the "Ship quality software......" heading 3. The first line reads, "Automatically......., execute TEXT,...." 4. Scroll down on the homepage to "insightful report" 5. The last line reads "with beautiful visulaizations" | https://cycluno.com/dashboard | No spelling error | Spelling errors in two different places | MINOR | LOW | BUG 07 | Chrome and Firefox WINDWOS 11 PRO STARLINK DELL 7280 Intel corei5 | Sadiq Balogun | 2026-02-26
Bug-08 | Navigation from "Get started for free" goes to "Sign in" instead of "Sign up / Registration Page" | - The 'Get Started for Free' call-to-action (CTA) button in the hero section is the primary conversion button on the page and is intended to drive new visitors toward creating a new account. - When the 'Get Started for Free' button is clicked, the user is redirected to the Sign In page (https://cycluno.com/login) rather than the Sign Up / Registration page (https://cycluno.com/register). This is incorrect behaviour. A first-time visitor clicking 'Get Started for Free' has no account yet and has expressed intent to register, sending them to the Sign In page instead creates immediate confusion, friction, and a broken user journey. | Navigate to Cycluno homepage Click on the "Get started for free" tab Observe result | https://cycluno.com/dashboard | Redirects the user to the "Sign-in" for existing users | "Get Started for Free" tab should redirect user to the "Sign up/ Register" page to get started as a new users just as the feauture implies | MAJOR | MEDIUM | BUG 08.mp4 | Firefox and Chrome Windows 11 MTN 5G WIFI LENOVO THINKPAD, I5 | Bisola Oyetade | 2026-02-26
Bug-09 | Links in the feauture section redirect to an error page on the dashboard | Links under "feauture" section in the footer tab are redirected to dashboard which shows an error message | 1 Enter the website URL (e.g., https://cycluno.com) 2 Scroll down to the footer 3 Find the features section 4 Click all four feautures listed (Design, Execute, Report, Bugbed) 5 Observe the result. | https://cycluno.com | The tabs in the footer should redirect to respective options | Redirected to dashboard showing the error message "dashboard issue - we ran into a problem loading your page" | MAJOR | MEDIUM | BUG 09.webm | Chrome and Firefox WindowsPC MTN 5G / Airtel pocket mifi HP Elitebook | Adu Victoria | 2026-02-26